# Project Plan 2 — Data Snooping in Deep Learning

Topic: measure how much of a model’s “improvement” from searching architectures + hyperparameters is real, and how much is just luck.

## The one fact everything grows from

A validation score is only a noisy guess at true performance

⇒ when I try many configurations and keep the best validation score, I keep the luckiest, not the best

⇒ that score is inflated, and the inflation grows the more I search.

I measure this, I don’t predict it: a sealed test set, opened once at the very end

⇒ gap = best-validation score − sealed-test score.

## What drives the gap (my four questions)

Each: state what I expect

⇒ let the data confirm or refute

⇒ report honestly, even against me. - more configurations searched (N)

⇒ bigger gap? - more label noise

⇒ bigger gap? - more model capacity

⇒ bigger gap? - which honest protocol (single split / k-fold / nested CV) shrinks it?

## Datasets — three points on one axis (signal strength)

- Synthetic lab (I generate it; truth known). Why: only generated data gives exact true labels ⇒ I can measure the gap exactly and inject known noise. This is where I earn the core results.

- UCI loan default (real, messy, stakes). Does the gap appear on its own? Consequence: how many bad loans get wrongly approved.

- Financial prices (^GSPC) — your suggestion. Signal ≈ 0 ⇒ the “edge” found by searching is almost all luck ⇒ the best-on-validation strategy collapses out-of-sample. Chronological (walk-forward) split. Consequence: money lost. The shocking warning.

One change I’d like to confirm: the clean set → synthetic.

To measure the gap I must compare the selected model against its true performance. On real data (loan included) the “true” performance is itself only an estimate from a finite test set

⇒ the gap I measure is blurred by the very noise I am trying to study. With a synthetic set I control the data-generating process, which buys three things real data cannot give: - exact truth — I can make the test set as large as I like (e.g. 100k rows)

⇒ the test score ≈ true performance with almost no sampling error, so the gap is measured exactly. - a signal dial — I can set the signal strength from easy (loan-like) down to near-random (finance-like)

⇒ all three datasets sit on one axis. - known noise — I can inject exactly-known label noise

⇒ this is what the noise question (does more noise widen the gap?) requires.

So synthetic is the only place I can measure the gap precisely and run controlled experiments; the loan and finance sets then test whether the same effect appears in the wild. The approved plan had the clean set as loan — this is the one change I’d like to confirm. Loan stays, as the real-stakes case. Net: three datasets on one signal axis.

## The instrument

A from-scratch MLP with backprop in NumPy (I derive backprop + the optimizer updates + L2 in the dissertation). Small validation set on purpose ⇒ noise high ⇒ snooping strong, as you noted. Test set untouched all project ⇒ reveals true performance.

## Workflow (one machine, all three datasets)

split → search N configs → keep best on validation → reveal once on sealed test → record the gap. Each experiment varies one knob.

## Headline figure

True performance of the selected config vs N, drawn next to its apparent (best-validation) score ⇒ expected: apparent keeps rising; true rises, plateaus, then turns down ⇒ search has an optimal budget, and past it more search buys a worse model and more false confidence.

## How I’ll work — core first, one milestone

I’ll build the core first and fast.

Near-term milestone — by ~6 July: the core. A from-scratch network that trains, plus the headline figure: true vs apparent accuracy as the number of searched configurations grows. This is a go/no-go gate — if the core proves technically unworkable, I’d rather find out now and adjust direction with you than in August. (A small or absent gap is not a failure — it’s an honest finding I’ll report; the gate is about technical viability, not dramatic results.)

After the gate, the same machine extends — with no new parts — to the remaining questions (label noise, model capacity, selection protocol) on the lab, then to the real loan and finance data. I’ll agree those dates with you once the core stands.

## What I’m asking you to approve

The direction — specifically the switch to a synthetic clean lab — and the ~6 July core milestone (the headline figure) as the go/no-go gate.

Feedback:

Very good idea to use synthetic dataset(s) because one can get more insight that way.

An interesting case is to construct a matrix of Gaussian samples. This is your X - each row is on synthetic 'sample'.

3 interesting cases:

- Random labels. No generalisation should be possible,but how well can you fit?

- Label each row j as  label_j = sign( X_{j,1})

- As 2, except after labelling, multiply the matrix X by a random isometry (you can research how to do that - it's good for your linear algebra). X' =XR , where R is a square matrix which is a rotation and (possibly) a reflection.

Now compare  nearest-neighbour, tree methods, logistic regression, and svm (all from sklearn) on these datasets.